Section 6 – General Conditions of Contract

Item	5

A	5

Contract and Interpretation	5

1	5

Definitions	5

2	6

Contract Documents	6

3	6

Interpretation	6

4	7

Communications	7

5	8

Law and Language	8

6	8

Corrupt Practices	8

B	8

Subject Matter of Contract	8

7	8

Scope of Works	8

8	9

Time for Commencement and Completion	9

9	9

Agency’s Responsibilities	9

10	9

Employer’s Responsibilities	9

C	10

Payment	10

11	10

Contract Price	10

12	10

Terms of Payment	10

13	11

Security Deposit	11

14	11

Taxes and Duties	11

D	12

Execution of the Works	12

15	12

Representatives	12

16	13

Work Program	13

17	14

Subcontracting	14

18	14

Design and Engineering	14

19	16

Procurement	16

20	17

Construction	17

21	21

Test and Inspection	21

22	24

Completion of the Works	24

23	25

Commissioning and Operational Acceptance	25

E	27

Guarantees and Liabilities	27

24	27

Completion Time Guarantee	27

25	27

Defect Liability	27

26	29

Functional Guarantees	29

27	29

Limitation of Liability	29

F	29

Risk Distribution	29

28	29

Transfer of Ownership	29

29	29

Care of Works	29

30	30

Loss of or Damage to Property; Accident or Injury to Workers; Indemnification	30

31	31

Insurance	31

32	33

Unforeseen Conditions	33

33	34

Change in Laws and Regulations	34

34	34

Force Majeure	34

G	35

Change in Contract Elements	35

35	35

Change in the Works	35

36	38

Extension of Time for Completion	38

37	39

Suspension	39

38	40

Termination	40

39	45

Assignment	45

H	45

Claims, Disputes and Arbitration	45

40	45

Agency’s Claims	45

41	47

Disputes and Arbitration	47

| Item |  |  |
| --- | --- | --- |
| A | Contract and Interpretation |
| 1 | Definitions | 1.1 The following words and expressions shall have the meanings hereby assigned to them: “Contract” means the Contract Agreement entered into between the Employer and the Agency, together with the Contract Documents referred to therein; they shall constitute the Contract, and the term “the Contract” shall in all such documents be construed accordingly. “Contract Documents” means the documents listed in Article 1.1 (Contract Documents) of the Contract Agreement (including any amendments thereto). “GCC” means the General Conditions of Contract. “SCC” means the Special Conditions of Contract. “day” means calendar day . “year” means 365 days. “month” means calendar month. “Party” means the Employer or the Agency, as the context requires. “Employer” means the person named as such in the SCC and includes the legal successors or permitted assigns of the Employer. “Project Manager” means the person appointed by the Employer in the manner provided in GCC Sub-Clause 15.1 (Project Manager) hereof and named as such in the SCC to perform the duties delegated by the Employer. “Agency” means the person(s) named as Agency in the Contract Agreement, and includes the legal successors or permitted assigns of the Agency. “Agency’s Representative” means any person nominated by the Agency and approved by the Employer in the manner provided in GCC Sub-Clause 15.2 (Agency’s Representative and Construction Manager) hereof to perform the duties delegated by the Agency. “Construction Manager” means the person appointed by the Agency’s Representative in the manner provided in GCC Sub-Clause 15.2.4. “Subcontract agency,” means any person to whom execution of any part of the Works, is sub-contracted directly or indirectly by the Agency, and includes its legal successors or permitted assigns. “Contract Price” means the sum specified in Article 2.1 (Contract Price) of the Contract Agreement, subject to such additions and adjustments thereto or deductions there from, as may be made pursuant to the Contract. “Works” means the Works to be carried out by the Agency under the Contract. “Site” means the land and other places upon which the Works are to be constructed, and such other land or places as may be specified in the Contract as forming part of the Site. “Effective Date” means the date of fulfillment of all conditions stated in Article 3 (Effective Date) of the Contract Agreement, upon which the period until the Time for Completion shall be counted from. “Time for Completion” means the time within which Completion of the Works as a whole (or of a part of the Works where a separate Time for Completion of such part has been prescribed) is to be attained, as referred to in GCC Clause 8 and in accordance with the relevant provisions of the Contract. “Completion” means that the Works (or a specific part thereof where specific parts are specified in the Contract) have been completed operationally and structurally and put in a clean condition, that all work in respect of construction of the Works or such specific part thereof has been completed, and that the Works or specific part thereof are ready for Commissioning as provided in GCC Clause 22 (Completion) hereof. “Commissioning” means the making operational of the Works or any part thereof by the Agency following Completion, which operation is to be carried out by the Agency as provided for in GCC Sub-Clause 23.1 (Commissioning) hereof. “Operational Acceptance” means the acceptance by the Employer of the Works (or any part of the Works where the Contract provides for acceptance of the Works in parts), which certifies the Agency’s fulfillment of the Contract in respect of deemed acceptance of the works in accordance with GCC Clause 23 (Commissioning and Operational Acceptance) hereof. “Defect Liability Period” means the period of validity of the warranties given by the Agency commencing at Completion of the Works or a part thereof, during which the Agency is responsible for defects with respect to the Works (or the relevant part thereof) as provided in GCC Clause 25 (Defect Liability) hereof. |
| 2 | Contract Documents | 2.1 Subject to Article 1.2 (Order of Precedence) of the Contract Agreement, all documents forming part of the Contract (and all parts thereof) are intended to be correlative, complementary and mutually explanatory. The Contract shall be read as a whole. |
| 3 | Interpretation | 3.1 In the Contract, except where the context requires otherwise: words indicating one gender include all genders; words indicating the singular also include the plural and words indicating the plural also include the singular; provisions including the word “agree”, “agreed” or “agreement” require the agreement to be record in writing; the word “tender” is synonymous with “bid”, “agency” with “bidder” and “tender documents” with “bidding documents”; and “written” or “in writing” means hand-written, type-written, printed or electronically made correspondence, and resulting in a permanent record. The marginal words and other headings shall not be taken into consideration in the interpretation of these Conditions. 3.2 Entire Agreement Subject to GCC Sub-Clause 16.4 hereof, the Contract constitutes the entire agreement between the Employer and Agency with respect to the subject matter of Contract and supersedes all communications, negotiations and agreements (whether written or oral) of parties with respect thereto made prior to the date of Contract. 3.5 Amendment No amendment or other variation of the Contract shall be effective unless it is in writing, is dated, expressly refers to the Contract, and is signed by a duly authorized representative of each party hereto. 3.6 Independent Agency The Agency shall be an independent agency performing the Contract. The Contract does not create any agency, partnership, joint venture or other joint relationship between the parties hereto. Subject to the provisions of the Contract, the Agency shall be solely responsible for the manner in which the Contract is performed. All employees, representatives or Sub agencies engaged by the Agency in connection with the performance of the Contract shall be under the complete control of the Agency and shall not be deemed to be employees of the Employer, and nothing contained in the Contract or in any subcontract awarded by the Agency shall be construed to create any contractual relationship between any such employees, representatives or Sub-agency and the Employer. 3.7 Non-Waiver 3.7.1 Subject to GCC Sub-Clause 3.7.2 below, no relaxation, forbearance, delay or indulgence by either party in enforcing any of the terms and conditions of the Contract or the granting of time by either party to the other shall prejudice, affect or restrict the rights of that party under the Contract, nor shall any waiver by either party of any breach of Contract operate as waiver of any subsequent or continuing breach of Contract. 3.7.2 Any waiver of a party’s rights, powers or remedies under the Contract must be in writing, must be dated and signed by an authorized representative of the party granting such waiver, and must specify the right and the extent to which it is being waived. 3.8 Severability If any provision or condition of the Contract is prohibited or rendered invalid or unenforceable, such prohibition, invalidity or unenforceability shall not affect the validity or enforceability of any other provisions and conditions of the Contract. |
| 4 | Communications | 4.1 Wherever these Conditions provide for the giving or issuing of approvals, certificates, consents, determinations, notices, requests and discharges, these communications shall be: in writing and delivered against receipt; and delivered, sent or transmitted to the address for the recipient’s communications as stated in the Contract Agreement. 4.2 When a certificate is issued to a Party, the certifier shall send a copy to the other Party. When a notice is issued to a Party, by the other Party or the Project Manager, a copy shall be sent to the Project Manager or the other Party, as the case may be. |
| 5 | Law and Language | 5.1 The Contract shall be governed by and interpreted in accordance with laws of India. 5.2 The ruling language of the Contract shall be English. 5.3 The language for communications shall be the ruling language. |
| 6 | Corrupt Practices | 6.1 The Recipient and Employers (including beneficiaries), as well as agency, suppliers, and agency under state and Centre financed contracts, observe the highest standard of ethics during the procurement and execution of such contracts. In pursuance of this policy, the programme defines, for the purposes of this provision, the terms set forth below as follows: “corrupt practice” means the offering, giving receiving, or soliciting, directly or indirectly, of anything of value to influence the action of any party in the procurement process or the execution of a contract; “fraudulent practice” means a misrepresentation or omission of facts in order to influence a procurement process or the execution of a contract; “collusive practices” means a scheme or arrangement between two or more Bidders, with or without the knowledge of the Recipient or Employer, designed to influence the action of any party in a procurement process or the execution of a contract; “coercive practices” means harming or threatening to harm, directly or indirectly, persons, or their property to influence their participation in a procurement process, or affect the execution of a contract; 6.2 ULB will reject a proposal for award if it determines that the Bidder recommended for award has, directly or through an agent, engaged in corrupt, fraudulent, collusive, or coercive practices in competing for the Contract; and 6.3 ULB will sanction a party or its successor, including declaring ineligible, either indefinitely or for a stated period of time, to participate in MPUSP-financed activities if it at any time it determines that a agency has, directly or through an agent, engaged in corrupt, fraudulent, collusive, or coercive practices in competing for, or in executing, a GOVERNMENT-financed contract. |
| B | Subject Matter of Contract |
| 7 | Scope of Works | 7.1 Unless otherwise expressly limited in the Employer’s Requirements, the Agency’s obligations cover the construction and commissioning of the Works in accordance with the plans, procedures, specifications, drawings, codes and any other documents as specified in the Section 5, Employer’s Requirements. Such specifications include, but are not limited to, the provision of supervision and engineering services; the supply of labor, materials, and Agency’s Equipment; construction utilities and supplies; temporary materials, structures and Works; transportation (including, without limitation, unloading and hauling to, from and at the Site); and storage, except for any supplies, works and services that will be provided or performed by the Employer, as set forth in the Contract Agreement. 7.2 The Agency shall, unless specifically excluded in the Contract, perform all such work and/or supply all such items and materials not specifically mentioned in the Contract but that can be reasonably inferred from the Contract as being required for attaining Completion of the Works as if such work and/or items and materials were expressly mentioned in the Contract. |
| 8 | Time for Commencement and Completion | 8.1 The Agency shall commence the Works within the period specified in the SCC and without prejudice to GCC Sub-Clause 24.2 hereof, the Agency shall thereafter proceed with the Works in accordance with the time schedule specified in the Contract Agreement. 8.2 The Agency shall attain Completion of Works or of a part where a separate time for Completion of such part is specified in the Contract, within the time stated in the SCC or within such extended time to which the Agency shall be entitled under GCC Clause 36 hereof. |
| 9 | Agency’s Responsibilities | 9.1 The Agency shall supply materials for, construct and complete the Works in accordance with the Contract. When completed, the Works should be fit for the purposes for which they are intended as defined in the Contract. 9.2 The Agency confirms that it has entered into this Contract on the basis of a proper examination of the data relating to the Works provided by the Employer, and on the basis of information that the Agency could have obtained from a visual inspection of the Site if access thereto was available and of other data readily available to it relating to the Works. The Agency acknowledges that any failure to acquaint itself with all such data and information shall not relieve it of its responsibility for properly completing the Works. 9.3 The Agency shall acquire and pay for all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings which such authorities or undertakings require the Agency to obtain in its name, and which are necessary for the performance of the Contract, and are not the responsibility of the Employer under GCC Sub-Clause 10.3 hereof. 9.4 The Agency shall comply with all laws in force where the Works are to be constructed. The laws will include all local, state, national or other laws that affect the performance of the Contract and bind upon the Agency. The Agency shall indemnify and hold harmless the Employer from and against any and all liabilities, damages, claims, fines, penalties and expenses of whatever nature arising or resulting from the violation of such laws by the Agency or its personnel, including the Sub-agency and their personnel, but without prejudice to GCC Sub-Clause 10.1 hereof. |
| 10 | Employer’s Responsibilities | 10.1 All information and/or data to be supplied by the Employer as described in the Contract Agreement shall be deemed to be accurate, except when the Employer expressly states otherwise. 10.2 The Employer shall be responsible for acquiring and providing legal and physical possession of the Site and access thereto, and for providing possession of and access to all other areas reasonably required for the proper execution of the Contract, including all requisite rights of way, as specified in the Contract Agreement. The Employer shall give full possession of and accord all rights of access thereto on or before the date(s) specified in the Contract Agreement. 10.3 The Employer shall acquire and pay for all permits, approvals and/or licenses from all local, state or national government authorities or public service undertakings in the country where the Site is located which (a) such authorities or undertakings require the Employer to obtain in the Employer’s name, (b) are necessary for the execution of the Contract, including those required for the performance by both the Agency and the Employer of their respective obligations under the Contract, and (c) are specified in the Contract Agreement. 10.4 If requested by the Agency, the Employer shall use its best endeavors to assist the Agency in obtaining in a timely and expeditious manner all permits, approvals and/or licenses necessary for the execution of the Contract from all local, state or national government authorities or public service undertakings that such authorities or undertakings require the Agency or Sub-agency or the personnel of the Agency or Sub-agency, as the case may be, to obtain. 10.5 In the event that the Employer shall be in breach of any of his obligations imposed by the Contract, then the additional cost reasonably incurred by the Agency in consequence thereof shall be added to the Contract Price. |
| C | Payment |
| 11 | Contract Price | 11.1 The Contract Price shall be as specified in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement. 11.2 Unless an escalation clause is provided for in the SCC, the Contract Price shall be a firm lump sum not subject to any alteration, except in the event of a Change in the nature, scope of Works necessitating the escalation or as otherwise provided in the Contract. 11.3 Subject to GCC Sub-Clauses 9.2, 10.1 and 32 hereof, the Agency shall be deemed to have satisfied itself as to the correctness and sufficiency of the Contract Price, which shall, except as otherwise provided for in the Contract, cover all its obligations under the Contract. |
| 12 | Terms of Payment | 12.1 The Contract Price shall be paid as specified in Article 5 (Contract Price and Terms of Payment) of the Contract Agreement and in the Appendix 1 (Terms and Procedures of Payment) to the Contract Agreement, which also outlines the procedures to be followed in making application for and processing payments. 12.2 No payment made by the Employer herein shall be deemed to constitute acceptance by the Employer of the Works or any part(s) thereof. 12.3 Payment shall be made as follows subject to the conditions relating to deduction of Income Tax, Sales Tax and Seigniorage etc. as applicable as on the date of payment. The payment shall be made for finished item of work The watch and ward for the safe storage of the pipes, specials and valves shall be arranged exclusively by the Agency, at his own cost. No extra payment will be made to the Agency for conveyance of the same to the work site from any temporary storage location selected/provided. |
| 13 | Security Deposit | 13.1 Issuance of Securities The Agency shall provide the securities specified below in favor of the Employer at the times, and in the amount, manner in the specified form . 13.2 Advance Payment Security – not used The Agency shall provide the securities specified below in favor of the Employer at the times, and in the amount, manner in the specified form. 13.3 Performance Security 13.3.1 The Agency shall, within fourteen (14) days of the notification of contract award, provide a security deposit for the due performance of the Contract in the amount specified in the SCC. 13.3.2 The security shall be denominated in the currency of the Contract, and shall be in the form of a fixed deposits or other form acceptable to the Employer as provided for in the bidding documents, as stipulated by the Employer in the SCC. 13.4 Unless otherwise specified in the SCC, the security shall be reduced by half on the date of the Completion of the Works, and shall become null and void, three hundred and sixty five (365) days after Completion of the Works; provided, however, that if the maintenance or Defects Liability Period has been extended on any part of the Works pursuant to GCC Sub-Clause 25.8 hereof, the Agency shall issue an additional security in an amount proportionate to the Contract Price of that part. The security shall be returned to the Agency immediately after its expiration, provided, however, that if the Agency, pursuant to GCC Sub-Clause 25.10, is liable for an extended maintenance or defect liability obligation, the performance security shall be extended for the period and up to the amount specified in the SCC. |
| 14 | Taxes and Duties | 14.1 Except as otherwise specifically provided for in the Contract, the Agency shall bear and pay all taxes, duties, levies and charges assessed on the Agency, its Sub-agency or their employees by all municipal, state or national government authorities in connection with the Works. 14.2 If any tax exemptions, reductions, allowances or privileges are available to the Agency in accordance with prevailing laws or notifications of the relevant authority, the Employer shall use its best endeavors to enable the Agency to benefit from any such tax savings to the maximum allowable extent. 14.3 For the purpose of the Contract, it is agreed that the Contract Price specified in Article 2 (Contract Price and Terms of Payment) of the Contract Agreement is based on the taxes, duties, levies and charges prevailing at the date of bid submission. If any rates of Tax are increased or decreased, a new Tax is introduced, an existing Tax is abolished, or any change in interpretation or application of any Tax occurs in the course of the performance of the Contract, which was or will be assessed on the Agency, Sub-agency or their employees in connection with performance of the Contract, an equitable adjustment of the Contract Price shall be made to fully take into account any such change by addition to the Contract Price or deduction there from, as the case may be, in accordance with GCC Clause 35 hereof. |
| D | Execution of the Works |
| 15 | Representatives | 15.1 Project Manager If the Project Manager is not named in the Contract, then within seven (7) days of the Effective Date, the Employer shall appoint and notify the Agency in writing of the name of the Project Manager. The Employer may from time to time appoint some other person as the Project Manager in place of the person previously so appointed, and shall give a notice of the name of such other person to the Agency without delay. No such appointment shall be made at such a time or in such a manner as to impede the progress of work on the Works. Such appointment shall only take effect upon receipt of such notice by the Agency. The Project Manager shall represent and act for the Employer at all times during the performance of the Contract. All notices, instructions, orders, certificates, approvals and all other communications under the Contract shall be given by the Project Manager, except as herein otherwise provided. All notices, instructions, information and other communications given by the Agency to the Employer under the Contract shall be given to the Project Manager, except as herein otherwise provided. 15.2 Agency’s Representative & Construction Manager 15.2.1 If the Agency’s Representative is not named in the Contract, then within seven (7) days of the Effective Date, the Agency shall appoint the Agency’s Representative and shall request the Employer in writing to approve the person so appointed. If the Employer makes no objection to the appointment within seven (7) days, the appointment of the Agency’s Representative shall be deemed to have been approved. If the Employer objects to the appointment within seven (7) days giving the reason therefore, then the Agency shall appoint a replacement within seven (7) days of such objection, and the foregoing provisions of this GCC Sub-Clause 15.2.1 shall apply thereto. 15.2.2 The Agency’s Representative shall represent and act for the Agency at all times during the performance of the Contract and shall give to the Project Manager all the Agency’s notices, instructions, information and all other communications under the Contract. All notices, instructions, information and all other communications given by the Employer or the Project Manager to the Agency under the Contract shall be given to the Agency’s Representative or, in his/her absence, his/her deputy, except as herein otherwise provided. The Agency shall not revoke the appointment of the Agency’s Representative without the Employer’s prior written consent, which shall not be unreasonably withheld. If the Employer consents thereto, the Agency shall appoint some other person as the Agency’s Representative, pursuant to the procedure set out in GCC Sub-Clause 15.2.1. 15.2.3 The Agency’s Representative may, subject to the approval of the Employer which shall not be unreasonably withheld, at any time delegate to any person any of the powers, functions and authorities vested in him or her. Any such delegation may be revoked at any time. Any such delegation or revocation shall be subject to a prior notice signed by the Agency’s Representative, and shall specify the powers, functions and authorities thereby delegated or revoked. No such delegation or revocation shall take effect unless and until a copy thereof has been delivered to the Employer and the Project Manager. Any act or exercise by any person of powers, functions and authorities so delegated to him or her in accordance with this GCC Sub-Clause 15.2.3 shall be deemed to be an act or exercise by the Agency’s Representative. 15.2.4 From the commencement of construction of Works at the Site until Completion, the Agency’s Representative shall appoint a suitable person as the Construction Manager. The Construction Manager shall supervise all work done at the Site by the Agency and shall be present at the Site throughout normal working hours except when on leave, sick or absent for reasons connected with the proper performance of the Contract. Whenever the Construction Manager is absent from the Site, the Agency’s Representative or the Construction Manager shall appoint a suitable person to act as the Construction Manager’s deputy. 15.2.5 The Employer may by notice to the Agency object to any representative or person employed by the Agency in the execution of the Contract who, in the reasonable opinion of the Employer, may behave inappropriately, may be incompetent or negligent, or may commit a serious breach of the Site regulations provided under GCC Sub-Clause 22.3. The Employer shall provide evidence of the same, whereupon the Agency shall remove such person from the Works. 15.2.6 If any representative or person employed by the Agency is removed in accordance with GCC Sub-Clause 15.2.5, the Agency shall, where required, promptly appoint a replacement. |
| 16 | Work Program | 16.1 Agency’s Organization The Agency shall supply to the Employer and the Project Manager a chart showing the proposed organization to be established by the Agency for carrying out construction of the Works within seven (7) days of the Effective Date. The chart shall include the identities of the key personnel and the Agency shall promptly inform the Employer and the Project Manager in writing of any revision or alteration to this organization chart. 16.2 Program of Performance Within seven (7) days after the Effective Date, the Agency shall submit to the Project Manager a detailed implementation program of work under the Contract, made in a form acceptable to the Project Manager and showing the sequence in which it proposes to carry out the works, as well as the date by which the Agency reasonably requires that the Employer shall have fulfilled its obligations under the Contract so as to enable the Agency to execute the Contract in accordance with the program and to achieve Completion, Commissioning and Acceptance of the Works in accordance with the Contract. The program so submitted by the Agency shall accord with the Time Schedule included in the Contract Agreement and any other dates and periods specified in the Contract. The Agency shall update and revise the program as and when appropriate or when required by the Project Manager, but without modification in the Times for Completion given in the SCC and any extension granted in accordance with GCC Clause 36, and shall submit all such revisions to the Project Manager. 16.3 Progress Report The Agency shall monitor progress of all the activities specified in the program referred to in GCC Sub-Clause 16.2 above, and supply a progress report to the Project Manager every month. The progress report shall be in a form acceptable to the Project Manager and shall indicate: (a) percentage completion achieved compared with the planned percentage completion for each activity; and (b) where any activity is behind the program, giving comments and likely consequences and stating the corrective action being taken. 16.4 Progress of Performance If at any time the Agency’s actual progress falls behind the program referred to in GCC Sub-Clause 16.2, or it becomes apparent that it will so fall behind, the Agency shall, at the request of the Employer or the Project Manager, prepare and submit to the Project Manager a revised program, taking into account the prevailing circumstances, and shall notify the Project Manager of the steps being taken to expedite progress so as to attain Completion of the Works within the Time for Completion under GCC Sub-Clause 8.2, any extension thereof entitled under GCC Sub-Clause 36.1, or any extended period as may otherwise be agreed upon between the Employer and the Agency. 16.5 Procedures The Contract shall be executed in accordance with the Contract Documents including the procedures given in the Forms and Procedures of the Employer’s Requirements. 16.6 The Agency may execute the Contract in accordance with its own standard project execution plans and procedures to the extent that they do not conflict with the provisions contained in the Contract. |
| 17 | Subcontracting | 17.1 The Agency may employ such Sub agencies as it may select at its discretion and as specified in the Contract, but such employment shall not relieve the Agency from any of its obligations, duties or responsibilities under the Contract. |
| 18 | Design and Engineering | 18.1 Specifications and Drawings The Agency shall execute the works in accordance with the contract drawings and specifications. The Agency shall be entitled to disclaim responsibility for any discrepancies, errors or omissions in the designs, data, drawing, specification or other document, or any modification thereof provided or designated by or on behalf of the Employer, by giving a notice of such disclaimer to the Project Manager. 18.2 Codes and Standards Wherever references are made in the Contract to codes and standards in accordance with which the Contract shall be executed, the edition or the revised version of such codes and standards current at the date twenty-eight (28) days prior to date of bid submission shall apply unless otherwise specified. During Contract execution, any changes in such codes and standards shall be applied subject to approval by the Employer and shall be treated in accordance with GCC Clause 35. 18.3 Approval/Review of Technical Documents by Project Manager 18.3.1 The Agency shall prepare or cause its Sub-agency to prepare, and furnish to the Project Manager the documents listed in the Appendix (List of Documents for Approval or Review) to the Contract Agreement for its approval or review as specified and in accordance with the requirements of GCC Sub-Clause 16.2 (Program of Performance). Any part of the Works covered by or related to the documents to be approved by the Project Manager shall be executed only after the Project Manager’s approval thereof. GCC Sub-Clauses 18.3.2 through 18.3.7 shall apply to those documents requiring the Project Manager’s approval, but not to those furnished to the Project Manager for its review only. 18.3.2 Within fourteen (14) days after receipt by the Project Manager of any document requiring the Project Manager’s approval in accordance with GCC Sub-Clause 18.3.1, the Project Manager shall either return one copy thereof to the Agency with its approval endorsed thereon or shall notify the Agency in writing of its disapproval thereof and the reasons therefore and the modifications that the Project Manager proposes. If the Project Manager fails to take such action within the said fourteen (14) days, then the said document shall be deemed to have been approved by the Project Manager. 18.3.3 The Project Manager shall not disapprove any document, except on the grounds that the document does not comply with the Contract or that it is contrary to good engineering practice. If the Project Manager disapproves a document, he shall specify the reasons for his decision. 18.3.4 If the Project Manager disapproves the document, the Agency shall modify the document and resubmit it for the Project Manager’s approval in accordance with GCC Sub-Clause 18.3.2. If the Project Manager approves the document subject to modification(s), the Agency shall make the required modification(s), whereupon the document shall be deemed to have been approved. 18.3.5 If any dispute or difference occurs between the Employer and the Agency in connection with or arising out of the disapproval by the Project Manager of any document and/or any modification(s) thereto that cannot be settled between the parties within a reasonable period, then such dispute or difference may be resolved through the disputes procedure in accordance with GCC Clause 41 hereof. 18.3.6 The Project Manager’s approval, with or without modification of the document furnished by the Agency, shall not relieve the Agency of any responsibility or liability imposed upon it by any provisions of the Contract except to the extent that any subsequent failure results from modifications required by the Project Manager. 18.3.7 The Agency shall not depart from any approved document unless the Agency has first submitted to the Project Manager an amended document and obtained the Project Manager’s approval thereof, pursuant to the provisions of this GCC Sub-Clause 18.3. 18.3.8If the Project Manager requests any change in any already approved document and/or in any document based thereon, the provisions of GCC Clause 35 shall apply to such request. |
| 19 | Procurement | 19.1 Materials Subject to GCC Sub-Clause 16.2, the Agency shall procure and transport all materials in an expeditious and orderly manner to the Site. 19.2 Employer-Supplied Materials If the Appendix 6 (Scope of Works and Supply by the Employer) to the Contract Agreement provides that the Employer shall furnish any specific materials or items to the Agency, the following provisions shall apply: 19.2.1 The Employer shall, at its own risk and expense, transport each item or materials to the place on or near the Site as agreed upon by the parties and make such item available to the Agency at the time specified in the program furnished by the Agency, pursuant to GCC Sub-Clause 16.2, unless otherwise mutually agreed. 19.2.2 Upon receipt of such item or materials, the Agency shall inspect the same visually and notify the Project Manager of any detected shortage, defect or default. The Employer shall immediately remedy any shortage, defect or default, or the Agency shall, if practicable and possible, at the request of the Employer, remedy such shortage, defect or default at the Employer’s cost and expense. After inspection, such item shall fall under the care, custody and control of the Agency. The provision of this GCC Sub-Clause 19.2.2 shall apply to any item supplied to remedy any such shortage or default or to substitute for any defective item, or shall apply to defective items that have been repaired. 19.2.3 The foregoing responsibilities of the Agency and its obligations of care, custody and control shall not relieve the Employer of liability for any undetected shortage, defect or default, nor place the Agency under any liability for any such shortage, defect or default whether under GCC Clause 25 or under any other provision of Contract. 19.2.4 Such materials or items shall be supplied for the purpose of contract only and the value of materials so supplied shall be deducted at the specified rates, as and when materials are consumed in items of work for which payments are being made. All such materials or items shall remain the absolute property of the Government and shall not be removed from the site, and all such-materials which are rendered surplus shall be returned by the agency at the place of issue at his own expense. Only such materials as are in good condition shall be taken back as determined by the Project Manager. 19.2.5 In case of materials incorporated in the schedule, proper daily account shall be kept by the agency. This account shall be open for inspection by the Project Manager at all reasonable times. The agency shall submit a monthly report to the Project Manager of consumption and balances of materials supplied by the Employer. If any such material, so issued does not tally with the progress of work or Employer’s account, the Agency shall be charged for such shortages at double the issue rate or double the market rate, whichever is more as on the date of such detection. 19.2.6 If, for any reason, the materials intended to be supplied by the Employer as mentioned in the Scope of Works and Supply by the Employer, could not be supplied so as to affect the timely progress of work, the agency shall be granted extension of time under GCC Clause 36. |
| 20 | Construction | 20.1 Setting Out/Supervision 20.1.1 Bench Mark (a) The Agency shall be responsible for the true and proper setting-out of the Works in relation to bench marks, reference marks and lines as stated in the Employers Requirements (Section 5) or as provided to the Agency in writing by or on behalf of the Employer. (b) If, at any time during the progress of construction of the Works, any error shall appear in the position, level or alignment of the Works, the Agency shall forthwith notify the Project Manager of such error and, at its own expense, immediately rectify such error to the reasonable satisfaction of the Project Manager. If such error is based on incorrect data provided in writing by or on behalf of the Employer, the expense of rectifying the same shall be borne by the Employer. 20.1.2 Agency’s Supervision The Agency shall give or provide all necessary superintendence during the construction of the Works, and the Construction Manager or its deputy shall be constantly on the Site to provide full-time superintendence of construction. The Agency shall provide and employ only technical personnel who are skilled and experienced in their respective callings and supervisory staff who are competent to adequately supervise the work at hand. 20.2 Labor 20.2.1 Engagement of Staff and Labor (a) Except as otherwise stated in the Specification, the Agency shall make arrangements for the engagement of all staff and labor, local or otherwise, and for their payment. (b) The Agency shall provide and employ on the Site in the construction of the Works such skilled, semi-skilled and unskilled labor as is necessary for the proper and timely execution of the Contract. The Agency is encouraged to use local labor that has the necessary skills. (c) The Agency shall be responsible for obtaining all necessary permit(s) from the appropriate authorities for the entry of all labor and personnel to be employed on the Site. The Employer will, if requested by the Agency, use his best endeavors in a timely and expeditious manner to assist the Agency in obtaining any local, state, national or government permission required for bringing in the Agency’s personnel. 20.2.2 Persons in the Service of Employer The Agency shall not recruit, or attempt to recruit, staff and labor from amongst the Employer’s Personnel. 20.2.3 Labor Laws (a) The Agency shall comply with all the relevant labor Laws applicable to the Agency’s Personnel, including Laws relating to their employment, health, safety, and welfare, and shall allow them all their legal rights. 20.2.4 Rates of Wages and Conditions of Labor (a) The Agency shall pay rates of wages, and observe conditions of labor, which are not lower than those established for the trade or industry where the work is carried out. If no established rates or conditions are applicable, the Agency shall pay rates of wages and observe conditions which are not lower than the general level of wages and conditions observed locally by employers whose trade or industry is similar to that of the Agency. (b) The Agency shall inform the Agency’s Personnel about their liability to pay personal income taxes in respect of such of their salaries, wages and allowances as are chargeable under the Laws for the time being in force, and the Agency shall perform such duties in regard to such deductions thereof as may be imposed on him by such Laws. 20.2.5 Working Hours (a) No work shall be carried out on the Site on locally recognized days of rest, or outside the normal working hours stated in the SCC, unless: (i) otherwise stated in the Contract, (ii) the Project Manager gives consent, or (iii) the work is unavoidable, or necessary for the protection of life or property or for the safety of the Works, in which case the Agency shall immediately advise the Project Manager. (b) If and when the Agency considers it necessary to carry out work at night or on public holidays so as to meet the Time for Completion and requests the Project Manager’s consent thereto, the Project Manager shall not unreasonably withhold such consent. (c) This Sub-Clause shall not apply to any work which is customarily carried out by rotary or double-shifts. 20.2.6 Facilities for Staff and Labor (a) Except as otherwise stated in the Specification, the Agency shall provide and maintain all necessary accommodation and welfare facilities for the Agency’s Personnel. The Agency shall also provide facilities for the Employer’s Personnel as stated in the Specification. (b) The Agency shall not permit any of the Agency’s Personnel to maintain any temporary or permanent living quarters within the structures forming part of the Permanent Works. 20.2.7 Health and Safety (a) The Agency shall at all times take all reasonable precautions to maintain the health and safety of the Agency’s Personnel, and ensure that suitable arrangements are made for all necessary welfare and hygiene requirements and for the prevention of epidemics. (b) The Agency shall send to the Engineer, details of any accident as soon as practicable after its occurrence. The Agency shall maintain records and make reports concerning health, safety and welfare of persons, and damage to property, as the Engineer may reasonably require. 20.2.8 Records of Agency’s Personnel The Agency shall keep accurate records of the Agency’s personnel, including the number of each class of Agency’s Personnel on the Site and the names, ages, genders, hours worked and wages paid to all workers. These records shall be summarized on a monthly basis in a form approved by the Project Manager and shall be available for inspection by the Project Manager until the Agency has completed all work. 20.2.9 Supply of Water The Agency shall, having regard to local conditions, provide on the Site an adequate supply of drinking and other water for the use of the Agency’s Personnel. 20.2.10 Measures against Insect and Pest Nuisance The Agency shall at all times take the necessary precautions to protect the Agency’s Personnel employed on the Site from insect and pest nuisance, and to reduce their danger to health. The Agency shall comply with all the regulations of the local health authorities, including use of appropriate insecticide. 20.2.11 Prohibition of All Forms of Forced or Compulsory Labor The agency shall not employ "forced or compulsory labor" in any form. "Forced or compulsory labor" consists of all work or service, not voluntarily performed, that is extracted from an individual under threat of force or penalty. 20.2.12 Prohibition of Harmful Child Labor The Agency shall not employ any child to perform any work that is economically exploitative, or is likely to be hazardous to, or to interfere with, the child's education, or to be harmful to the child's health or physical, mental, spiritual, moral, or social development. 20.3 Agency’s Equipment 20.3.1 All Agency’s Equipment brought by the Agency onto the Site shall be deemed to be intended to be used exclusively for the execution of the Contract. The Agency shall not remove the same from the Site without the Project Manager’s consent that such Agency’s Equipment is no longer required for the execution of the Contract. 20.3.2 Unless otherwise specified in the Contract, upon completion of the Works, the Agency shall remove from the Site all Equipment brought by the Agency onto the Site and any surplus materials remaining thereon. 20.4 Site Regulations and Safety The Employer and the Agency shall establish Site regulations setting out the rules to be observed in the execution of the Contract at the Site and shall comply therewith. The Agency shall prepare and submit to the Employer, with a copy to the Project Manager, proposed Site regulations for the Employer’s approval, which approval shall not be unreasonably withheld. Such Site regulations shall include, but shall not be limited to, rules in respect of security, safety of the Works and sanitation, medical care, and fire prevention. 20.5 Opportunities for Other Agency 20.5.1 The Agency shall, upon written request from the Employer or the Project Manager, give all reasonable opportunities for carrying out the work by any other agency employed by the Employer on or near the Site. 20.5.2 The Agency shall also arrange to perform its work so as to minimize, to the extent possible, interference with the work of other agency. The Project Manager shall determine the resolution of any difference or conflict that may arise between the Agency and other agency and the workers of the Employer in regard to their work. 20.5.3 The Agency shall notify the Project Manager promptly of any defects in the other agencies work that come to its notice, and that could affect the Agency’s work. The Project Manager shall determine the corrective measures, if any, required to rectify the situation after inspection of the Works. Decisions made by the Project Manager shall be binding on the Agency. 20.6 Emergency Work If, by reason of an emergency arising in connection with and during the execution of the Contract, any protective or remedial work is necessary as a matter of urgency to prevent damage to the Works, the Agency shall immediately carry out such work. If the Agency is unable or unwilling to do such work immediately, the Employer may do or cause such work to be done as the Employer may determine is necessary in order to prevent damage to the Works. In such event the Employer shall, as soon as practicable after the occurrence of any such emergency, notify the Agency in writing of such emergency, the work done and the reasons therefore. If the work done or caused to be done by the Employer is work that the Agency was liable to do at its own expense under the Contract, the reasonable costs incurred by the Employer in connection therewith shall be paid by the Agency to the Employer. Otherwise, the cost of such remedial work shall be borne by the Employer. 20.7 Site Clearance and Maintaining Access 20.7.1 Site Clearance in Course of Performance In the course of carrying out the Contract, the Agency shall keep the Site reasonably free from all unnecessary obstruction, store or remove any surplus materials, clear away any wreckage, rubbish or temporary works from the Site, and remove any Agency’s Equipment no longer required for execution of the Contract. 20.7.2 Maintaining Right of Way and Access to Properties In the course of carrying out the Contract, the Agency take whatever steps are necessary to maintain rights of way open and facilitate access to properties which are affected by the works. 20.7.3 Clearance of Site after Completion After Completion of all parts of the Works, the Agency shall clear away and remove all wreckage, rubbish and debris of any kind from the Site, and shall leave the Site and Works in a clean and safe condition. 20.8 Watching and Lighting The Agency shall provide and maintain at its own expense all lighting, fencing, and watching when and where necessary for the proper execution and the protection of the Works, or for the safety of the owners and occupiers of adjacent property and for the safety of the public. |
| 21 | Test and Inspection | 21.1 All work under or in the course of execution or executed in pursuance of the contract shall at all times be open to the inspection of the Project Manager. The Agency shall at all times during the usual working hours, and at all other times, at which reasonable notice of the intention of the Project Manager to visit the work shall have been given to the Agency, have either himself or a responsible and duly accredited agent present to receive inspections and instructions from the Project Manager. Instructions given to the agency's agent shall be considered to have the same force as if they had been given to the agency himself. 21.2 The Agency shall at its own expense carry out at the place of manufacture and/or on the Site all such tests and/or inspections of the Works as are specified in the Contract. 21.3 The Employer and the Project Manager or their designated representatives shall be entitled to attend the aforesaid test and/or inspection, provided that the Employer shall bear all costs and expenses incurred in connection with such attendance including, but not limited to, all traveling expenses. 21.4 Whenever the Agency is ready to carry out any such test and/or inspection, the Agency shall give a reasonable advance notice of such test and/or inspection and of the place and time thereof to the Project Manager. The Agency shall obtain from any relevant third party or manufacturer any necessary permission or consent to enable the Employer and the Project Manager or their designated representatives to attend the test and/or inspection. 21.5 The Agency shall provide the Project Manager with a certified report of the results of any such test and/or inspection. If the Employer or Project Manager or their designated representatives fails to attend the test and/or inspection, or if it is agreed between the parties that such persons shall not do so, then the Agency may proceed with the test and/or inspection in the absence of such persons, and may provide the Project Manager with a certified report of the results thereof. 21.6 The Project Manager may require the Agency to carry out any test and/or inspection not required by the Contract, provided that the Agency’s reasonable costs and expenses incurred in the carrying out of such test and/or inspection shall be added to the Contract Price. Further, if such test and/or inspection impede the progress of work on the Works and/or the Agency’s performance of its other obligations under the Contract, due allowance will be made in respect of the Time for Completion and the other obligations so affected. 21.7 If any material or part of the Works fails to pass any test and/or inspection, the Agency shall either rectify or replace such material or part of the Works and shall repeat the test and/or inspection upon giving a notice under GCC Sub-Clause 21.3. 21.8 If any dispute or difference of opinion shall arise between the parties in connection with or arising out of the test and/or inspection of materials or part of the Works that cannot be settled between the parties within a reasonable period of time, it may be referred to the disputes process in accordance with GCC Clause 41. 21.9 The Agency shall afford the Employer and the Project Manager, at the Employer’s expense, access at any reasonable time to any place where the Works are being carried out, in order to inspect the progress and the manner of manufacture or construction, provided that the Project Manager shall give the Agency a reasonable prior notice. 21.10 The Agency agrees that neither the execution of a test and/or inspection of the Works, nor the attendance by the Employer or the Project Manager, nor the issue of any test certificate pursuant to GCC Sub-Clause 21.4, shall release the Agency from any other responsibilities under the Contract. 21.11 No part of the Works or foundations shall be covered up on the Site without the Agency carrying out any test and/or inspection required under the Contract. The Agency shall give a reasonable notice to the Project Manager whenever any such parts of the Works or foundations are ready or about to be ready for test and/or inspection; such test and/or inspection and notice thereof shall be subject to the requirements of the Contract. 21.12 The Agency shall give not less than five days notice in writing to the Project Manager in order to obtain consent before covering up or otherwise placing beyond the reach of measurement any part of the Works or foundations, in order that the same may be measured, and correct dimensions thereof be taken before the same is so covered up or placed beyond the reach of measurement. If any Works shall be covered up or placed beyond the reach of measurement without such notice having been given, or consent obtained, the same shall be uncovered at the agency's expenses or in default thereof, no payment or allowance shall be made for such work or the materials with which the same was executed. 21.13 The Agency shall uncover any part of the Works or foundations, or shall make openings in or through the same as the Project Manager may from time to time require at the Site, and shall reinstate and make good such part or parts. If any parts of the Works or foundations have been covered up at the Site after compliance with the requirement of GCC Sub-Clause 21.10 and are found to be executed in accordance with the Contract, the expenses of uncovering, making openings in or through, reinstating, and making good the same shall be borne by the Employer, and the Time for Completion shall be reasonably adjusted to the extent that the Agency has thereby been delayed or impeded in the performance of any of its obligations under the Contract. 21.14 Quality Assurance and Quality Control Identifying Defects: The Engineer-in-Charge shall check the Agency’s work and notify the Agency of any Defects that are found. Such checking shall not affect the Agency’s responsibilities. The Engineer-in-Charge may instruct the Agency to verify the Defect and to uncover and test any work that the Engineer considers may be a Defect. Tests: If the Engineer-in-Charge instructs the Agency to carry out a test not specified in the Specification to check whether any work has a Defect and the Agency shall pay for the test and any samples. Correction of Defects: The Engineer-in-Charge shall give notice to the Agency of any Defects before the end of the Defects Liability Period, which begins on Completion. The defects liability period shall be extended for as long as defects remain to be corrected by the Agency. Every time notice of a Defect is given, the Agency shall correct the notified defect within the length of time specified by the Engineer-in-Charge’s notice. Uncorrected Defects: If the agency has not corrected the defect within the time specified in the Engineer-in-Charge’s notice, the Engineer-in-Charge will assess the cost of having the defect corrected and the agency will pay this amount. The Engineer-in-Charge may also introduce check lists which shall be kept in Bound registers by the construction supervision staff. The agency may be required to fill up these lists in the first instance and shall be subsequently checked by the Construction / Quality Control engineers. Quality Control: In addition to the normal inspection by the regular staff in charge of the Construction of work, the work will also be inspected by the authorities competent to inspect the works or by the State or District level Vigilance Cell Unit and any other authorised external Agency if any sub-standard work or excess payments are noticed with reference to measurement books etc., during inspection, action will be taken based on their observations and these will be effected by the Engineer-in-Charge of the execution of the work. For all works costing more than Rs.5.00 Crores the Agency shall submit quality plan and also show proof of owning quality lab or tie-up with an established quality lab. Design and Supervision arrangement shall be made for preparation of Detailed Designs and Construction Supervision including assuring quality of works before, during and after the construction of the works and their recommendations shall be binding on the agency. Design shall be provided by the agency and supervision arrangements shall be made by the ULB. Supervision shall be done by the ULB Engineer in charge. ULB shall have right to amend designs and estimates before approval, The agency shall prepare a QA plan for the works with the assistance of the Engineer in Charge appointed by ULB for the civil works. The preparations for the work, the quality of materials, quality of work during progress and the finished work will be supervised, monitored and inspected by Engineer in Charge and the agency can proceed with the subsequent stages of work only on clearance of the appropriate previous stages by the Engineer in Charge. Payments will not be released to agency unless certified by the Engineer in Charge. |
| 22 | Completion of the Works | 22.1 As soon as the Works or any part thereof has, in the opinion of the Agency, been completed operationally and structurally and put in a tight and clean condition as specified in the Employer’s Requirements, excluding minor items not materially affecting the operation or safety of the Works, the Agency shall so notify the Employer in writing. 22.2 As soon as all Works or any part thereof is ready for Commissioning, the Agency shall so notify the Project Manager in writing. 22.3 The Project Manager shall, within fourteen (14) days after receipt of the Agency’s notice under GCC Sub-Clause 22.2, either issue a Completion Certificate in the form specified in the Employer’s Requirements (Forms and Procedures), stating that the Works or that part thereof have reached Completion as of the date of the Agency’s notice under GCC Sub-Clause 22.2, or notify the Agency in writing of any defects and/or deficiencies. If the Project Manager notifies the Agency of any defects and/or deficiencies, the Agency shall then correct such defects and/or deficiencies, and shall repeat the procedure described in GCC Sub-Clause 22.2. If the Project Manager is satisfied that the Works or that part thereof have reached Completion, the Project Manager shall, within seven (7) days after receipt of the Agency’s repeated notice, issue a Completion Certificate stating that the Works or that part thereof have reached Completion as of the date of the Agency’s repeated notice. If the Project Manager is not so satisfied, then it shall notify the Agency in writing of any defects and/or deficiencies within seven (7) days after receipt of the Agency’s repeated notice, and the above procedure shall be repeated. 22.4 If the Project Manager fails to issue the Completion Certificate and fails to inform the Agency of any defects and/or deficiencies within fourteen (14) days after receipt of the Agency’s notice under GCC Sub-Clause 22.2 or within seven (7) days after receipt of the Agency’s repeated notice under GCC Sub-Clause 22.3, or if the Employer makes use of the Works or part thereof, then the Works or that part thereof shall be deemed to have reached Completion as of the date of the Agency’s notice or repeated notice, or as of the Employer’s use of the Works, as the case may be. 22.5 As soon as possible after Completion, the Agency shall complete all outstanding minor items so that the Works are fully in accordance with the requirements of the Contract, failing which the Employer will undertake such completion and deduct the costs thereof from any monies owing to the Agency. 22.6 Upon Completion and Acceptance, the Agency shall commence operation and maintenance of the works in accordance with GCC Clause 23 and for the period specified in the SCC. During the maintenance period, the Agency will be responsible for the care and custody of the Works or the relevant part thereof, together with the risk of loss or damage thereto except that arising out of normal wear and tear. |
| 23 | Commissioning and Operational Acceptance | 23.1 Commissioning 23.1.1 Commissioning of the Works or any part thereof shall be commenced by the Agency immediately after issue of the Completion Certificate by the Project Manager, pursuant to GCC Sub-Clause 22.5. 23.2 Operational Acceptance 23.2.1 Subject to GCC Sub-Clause 23.4 below, Operational Acceptance shall occur in respect of the Works or any part thereof when (a) the Agency has paid the liquidated damages specified in GCC Sub-Clause 24.2 hereof; and (d) any minor items mentioned in GCC Sub-Clause 22.5 hereof relevant to the Works or that part thereof have been completed. 23.3 Partial Acceptance 23.3.1 If the Contract specifies that Completion and Commissioning shall be carried out in respect of parts of the Works, the provisions relating to Completion and Commissioning shall apply to each such part of the Works individually, and the Operational Acceptance Certificate shall be issued accordingly for each such part of the Works. 23.3.2 If a part of the Works comprises Works such as buildings or roads, for which no Commissioning is required, then the Project Manager shall issue the Operational Acceptance Certificate for such facility when it attains Completion, provided that the Agency shall thereafter complete any outstanding minor items that are listed in the Operational Acceptance Certificate. 23.4 Delayed Commissioning 23.4.1 In the event that the Agency is unable to proceed with the Commissioning of the Works pursuant to Sub-Clause 23.1, for reasons attributable to the Employer either on account of non availability of other Works under the responsibilities of other agency(s), or for reasons beyond the Employer’s control, the provisions leading to “deemed” completion of activities such as Completion, pursuant to GCC Sub-Clause 22.4, and Operational Acceptance, pursuant to GCC Sub-Clause 23.2, and Agency’s obligations regarding Defect Liability Period, pursuant to GCC Sub-Clause 25.2, and Care of Works, pursuant to GCC Sub-Clause 27.1, and GCC Clause 28, Suspension, shall not apply. In this case, the following provisions shall apply. 23.4.2 When the Agency is notified by the Project Manager that he will be unable to proceed with the activities and obligations pursuant to above Sub-Clause 9.1, the Agency shall be entitled to the following: (a) the Time of Completion shall be extended for the period of suspension without imposition of liquidated damages pursuant to GCC Sub-Clause 24.2; (b) payments due to the Agency in accordance with the provision specified in the Appendix (Terms and Procedures of Payment) to the Contract Agreement, which would not have been payable in normal circumstances due to non-completion of the subject activities, shall be released to the Agency against submission of a security in the form of a bank guarantee of equivalent amount acceptable to the Employer, and which shall become null and void when the Agency will have complied with its obligations regarding those payments, subject to the provision of Sub-Clause 23.4.3 below; (c) the expenses towards the above security and extension of other securities under the contract, of which validity needs to be extended, shall be reimbursed to the Agency by the Employer; (d) the additional charges towards the care of the Works pursuant to GCC Sub-Clause 28 shall be reimbursed to the Agency by the Employer for the period between the notification mentioned above and the notification mentioned in Sub-Clause 23.4.3 below. The provision of GCC Sub-Clause 29.1 shall apply to the Works during the same period. 23.4.3 When the Agency is notified by the Project Manager that the plant is ready for Commissioning, the Agency shall proceed without delay in performing all the specified activities and obligations under the contract. |
| E | Guarantees and Liabilities |
| 24 | Completion Time Guarantee | 24.1 The Agency guarantees that it shall attain Completion of the Works (or a part for which a separate time for completion is specified) within the Time for Completion specified in the SCC pursuant to GCC Sub-Clause 8.2, or within such extended time to which the Agency shall be entitled under GCC Clause 36 hereof. 24.2 If the Agency fails to attain Completion of the Works or any part thereof within the Time for Completion or any extension thereof under GCC Clause 36, the Agency shall pay to the Employer liquidated damages in the amount specified in the SCC as a percentage rate of the Contract Price or the relevant part thereof. The aggregate amount of such liquidated damages shall in no event exceed the amount specified as “Maximum” in the SCC as a percentage rate of the Contract Price. Once the “Maximum” is reached, the Employer may consider termination of the Contract, pursuant to GCC Sub-Clause 38.1. Such payment shall completely satisfy the Agency’s obligation to attain Completion of the Works or the relevant part thereof within the Time for Completion or any extension thereof under GCC Clause 36. The Agency shall have no further liability whatsoever to the Employer in respect thereof. However, the payment of liquidated damages shall not in any way relieve the Agency from any of its obligations to complete the Works or from any other obligations and liabilities of the Agency under the Contract. Save for liquidated damages payable under this GCC Sub-Clause 24.2, the failure by the Agency to attain any milestone or other act, matter or thing by any date specified in the Appendix (Time Schedule) to the Contract Agreement and/or other program of work prepared pursuant to GCC Sub-Clause 16.2 shall not render the Agency liable for any loss or damage thereby suffered by the Employer. |
| 25 | Defect Liability | 25.1 The Agency warrants that the Works or any part thereof shall be free from defects in the engineering, materials and workmanship of the Works executed. 25.2 The Defect Liability Period shall be one year from the date of Operational Acceptance of the Works (or any part thereof), unless specified otherwise in the SCC, or pursuant to GCC Sub-Clause 25.10. 25.3 If during the Defect Liability Period any defect should be found in the design, engineering, materials and workmanship of the Works executed by the Agency, the Agency shall promptly, in consultation and agreement with the Employer regarding appropriate remedying of the defects, and at its cost, repair, replace or otherwise make good as the Agency shall determine at its discretion, such defect as well as any damage to the Works caused by such defect. The Agency shall not be responsible for the repair, replacement or making good of any defect or of any damage to the Works arising out of normal wear and tear. 25.4 The Agency’s obligations under this GCC Clause 25 shall not apply to: (a) any materials that are supplied by the Employer under GCC Sub-Clause 19.2, are normally consumed in operation, or have a normal life shorter than the Defect Liability Period stated herein; (b) any designs, specifications or other data designed, supplied or specified by or on behalf of the Employer or any matters for which the Agency has disclaimed responsibility herein; or (c) any other materials supplied or any other work executed by or on behalf of the Employer, except for the work executed by the Employer under GCC Sub-Clause 25.8. 25.5 The Employer shall give the Agency a notice stating the nature of any such defect together with all available evidence thereof, promptly following the discovery thereof. The Employer shall afford all reasonable opportunity for the Agency to inspect any such defect. 25.6 The Employer shall afford the Agency all necessary access to the Works and the Site to enable the Agency to perform its obligations under this GCC Clause 25. The Agency may, with the consent of the Employer, remove from the Site any part of the Works that are defective if the nature of the defect, and/or any damage to the Works caused by the defect, is such that repairs cannot be expeditiously carried out at the Site. 25.7 If the repair, replacement or making good is of such a character that it may affect the efficiency of the Works or any part thereof, the Employer may give to the Agency a notice requiring that tests of the defective part of the Works shall be made by the Agency immediately upon completion of such remedial work, whereupon the Agency shall carry out such tests. If such part fails the tests, the Agency shall carry out further repair, replacement or making good, as the case may be, until that part of the Works passes such tests. The tests shall be agreed upon by the Employer and the Agency. 25.8 If the Agency fails to commence the work necessary to remedy such defect or any damage to the Works caused by such defect within a reasonable time (which shall in no event be considered to be less than fifteen (15) days), the Employer may, following notice to the Agency, proceed to do such work, and the reasonable costs incurred by the Employer in connection therewith shall be paid to the Employer by the Agency or may be deducted by the Employer from any monies due the Agency or claimed under the Performance Security. 25.9 If the Works or any part thereof cannot be used by reason of such defect and/or making good of such defect, the Defect Liability Period of the Works or such part, as the case may be, shall be extended by a period equal to the period during which the Works or such part cannot be used by the Employer because of any of the aforesaid reasons. 25.10 Except as provided in GCC Clauses 25 and 30, the Agency shall be under no liability whatsoever and howsoever arising, and whether under the Contract or at law, in respect of defects in the Works or any part thereof, the Plant, design or engineering or work executed that appear after Completion of the Works or any part thereof, except where such defects are the result of the gross negligence, fraud, criminal or willful action of the Agency. 25.11 In addition, any such component of the Works and during the period of time as may be specified in the SCC shall be subject to an extended Defect Liability Period. Such obligation of the Agency shall be in addition to the Defect Liability Period specified under GCC Sub-Clause 25.2. |
| 26 | Functional Guarantees | 26.1 The Agency guarantees that during the Guarantee Test, the Facilities and all parts thereof shall attain the Functional Guarantees specified in the Appendix (Functional Guarantees) to the Contract Agreement, subject to and upon the conditions therein specified. 26.2 If, for reasons attributable to the Agency, the minimum level of the Functional Guarantees specified in the Appendix (Functional Guarantees) to the Contract Agreement are not met either in whole or in part, the Agency shall at its cost and expense make such changes, modifications and/or additions to the Works or any part thereof as may be necessary to meet at least the minimum level of such Guarantees. |
| 27 | Limitation of Liability | 27.1 Except in cases of criminal negligence or willful misconduct, (a) the Agency shall not be liable to the Employer, whether in contract, tort, or otherwise, for any indirect or consequential loss or damage, loss of use, loss of production, or loss of profits or interest costs, provided that this exclusion shall not apply to any obligation of the Agency to pay liquidated damages to the Employer and (b) the aggregate liability of the Agency to the Employer, whether under the Contract, in tort or otherwise, shall not exceed a multiple of the Contract Price specified in the SCC or, if a multiple is not so specified, the total Contract Price, provided that this limitation shall not apply to the cost of repairing or replacing defective equipment, or to any obligation of the Agency to indemnify the Employer with respect to patent infringement. |
| F | Risk Distribution |
| 28 | Transfer of Ownership | 28.1 Responsibility for care and custody of the Works and Equipment together with the risk of loss or damage thereto shall remain with the Agency pursuant to GCC Clause 29 (Care of Works) hereof until Completion of the Works or part of the Works. 28.2 Ownership of the Agency’s Equipment used by the Agency and its Sub-agency in connection with the Contract shall remain with the Agency or its Sub-agency. |
| 29 | Care of Works | 29.1 The Agency shall be responsible for the care and custody of the Works or any part thereof until the date of Completion of the Works pursuant to GCC Clause 22 or, where the Contract provides for Completion of the Works in parts, until the date of Completion of the relevant part, and shall make good at its own cost any loss or damage that may occur to the Works or the relevant part thereof from any cause whatsoever during such period. The Agency shall also be responsible for any loss or damage to the Works caused by the Agency or its Sub-agency in the course of any work carried out, pursuant to GCC Clause 23. Notwithstanding the foregoing, the Agency shall not be liable for any loss or damage to the Works or that part thereof caused by reason of any of the matters specified or referred to in paragraphs (a), (b) and (c) of GCC Sub-Clauses 29.2. 29.2 If any loss or damage occurs to the Works or any part thereof or to the Agency’s temporary Works by reason of (a) nuclear reaction, nuclear radiation, radioactive contamination, pressure wave caused by aircraft or other aerial objects, or any other occurrences that an experienced agency could not reasonably foresee, or if reasonably foreseeable could not reasonably make provision for or insure against, insofar as such risks are not normally insurable on the insurance market and are mentioned in the general exclusions of the policy of insurance, including War Risks and Political Risks, taken out under GCC Clause 31 hereof; or (b) any use or occupation by the Employer or any third party other than a Sub-agency, authorized by the Employer of any part of the Works; or (c) any use of or reliance upon any design, data or specification provided or designated by or on behalf of the Employer, or any such matter for which the Agency has disclaimed responsibility herein, the Employer shall pay to the Agency all sums payable in respect of the Works executed, notwithstanding that the same be lost, destroyed or damaged, and will pay to the Agency the replacement value of all temporary Works and all parts thereof lost, destroyed or damaged. 29.3 The Agency shall be liable for any loss of or damage to any Agency’s Equipment, or any other property of the Agency used or intended to be used for purposes of the Works, except (i) as mentioned in GCC Sub-Clause 29.2 with respect to the Agency’s temporary Works, and (ii) where such loss or damage arises by reason of any of the matters specified in GCC Sub-Clauses 29.2 (b) and (c). |
| 30 | Loss of or Damage to Property; Accident or Injury to Workers; Indemnification | 30.1 Subject to GCC Sub-Clause 30.3, the Agency shall indemnify and hold harmless the Employer and its employees and officers from and against any and all suits, actions or administrative proceedings, claims, demands, losses, damages, costs, and expenses of whatsoever nature, including attorney’s fees and expenses, in respect of the death or injury of any person or loss of or damage to any property other than the Works whether accepted or not, arising in connection with the construction of the Works and by reason of the negligence of the Agency or its Sub agencies, or their employees, officers or agents, except any injury, death or property damage caused by the negligence of the Employer, its agencies, employees, officers or agents. 30.2 If any proceedings are brought or any claim is made against the Employer that might subject the Agency to liability under GCC Sub-Clause 30.1, the Employer shall promptly give the Agency a notice thereof and the Agency may at its own expense and in the Employer’s name conduct such proceedings or claim and any negotiations for the settlement of any such proceedings or claim. If the Agency fails to notify the Employer within twenty-eight (28) days after receipt of such notice that it intends to conduct any such proceedings or claim, then the Employer shall be free to conduct the same on its own behalf. Unless the Agency has so failed to notify the Employer within the twenty-eight (28) day period, the Employer shall make no admission that may be prejudicial to the defense of any such proceedings or claim. The Employer shall, at the Agency’s request, afford all available assistance to the Agency in conducting such proceedings or claim, and shall be reimbursed by the Agency for all reasonable expenses incurred in so doing. 30.3 The Employer shall indemnify and hold harmless the Agency and its employees, officers and Sub-agency from any liability for loss of or damage to property of the Employer, other than the Works not yet taken over, that is caused by fire, explosion or any other perils, in excess of the amount recoverable from insurances procured under GCC Clause 31, provided that such fire, explosion or other perils were not caused by any act or failure of the Agency. 30.4 The party entitled to the benefit of an indemnity under this GCC Clause 30 shall take all reasonable measures to mitigate any loss or damage which has occurred. If the party fails to take such measures, the other party’s liabilities shall be correspondingly reduced. |
| 31 | Insurance | 31.1 To the extent specified in the Appendix (Insurance Requirements) to the Contract Agreement, the Agency shall at its expense take out and maintain in effect, or cause to be taken out and maintained in effect, during the performance of the Contract, the insurances set forth below in the sums and with the deductibles and other conditions specified in the said Appendix. The identity of the insurers and the form of the policies shall be subject to the approval of the Employer, who should not unreasonably withhold such approval. (b) Construction All Risks Insurance Covering physical loss or damage to the Works at the Site, occurring prior to Completion of the Works, with an extended maintenance coverage for the Agency’s liability in respect of any loss or damage occurring during the Maintenance and Defect Liability Period while the Agency is on the Site for the purpose of performing its obligations during the Maintenance and Defect Liability Period. (c) Third Party Liability Insurance Covering bodily injury or death suffered by third parties including the Employer’s personnel, and loss of or damage to property occurring in connection with the construction of the Works. (d) Automobile Liability Insurance Covering use of all vehicles used by the Agency or its Sub-agency, whether or not owned by them, in connection with the execution of the Contract. (e) Workers’ Compensation In accordance with statutory requirements. (f) Employer’s Liability In accordance with statutory requirements. (g) Other Insurances Such other insurances as may be specifically agreed upon by the parties hereto as listed in the Appendix (Insurance Requirements) to the Contract Agreement. 31.2 The Employer shall be named as co-insured under all insurance policies taken out by the Agency pursuant to GCC Sub-Clause 31.1, except for the Third Party Liability, Workers’ Compensation and Employer’s Liability Insurances, and the Agency’s Sub-agency shall be named as co-insured under all insurance policies taken out by the Agency pursuant to GCC Sub-Clause 31.1 except for Workers’ Compensation and Employer’s Liability Insurances. All insurers’ rights of subrogation against such co-insured for losses or claims arising out of the performance of the Contract shall be waived under such policies. 31.3 The Agency shall, in accordance with the provisions of the Appendix (Insurance Requirements) to the Contract Agreement, deliver to the Employer certificates of insurance or copies of the insurance policies as evidence that the required policies are in full force and effect. The certificates shall provide that no less than twenty-one (21) days’ notice shall be given to the Employer by insurers prior to cancellation or material modification of a policy. 31.4 The Agency shall ensure that, where applicable, its Sub-agency(s) shall take out and maintain in effect adequate insurance policies for their personnel and vehicles and for work executed by them under the Contract, unless such Sub-agency are covered by the policies taken out by the Agency. 31.5 The Employer shall at its expense take out and maintain in effect during the performance of the Contract those insurances specified in the Appendix (Insurance Requirements) to the Contract Agreement, in the sums and with the deductibles and other conditions specified in the said Appendix. The Agency and the Agency’s Sub-agency shall be named as co-insured under all such policies. All insurers’ rights of subrogation against such co-insured for losses or claims arising out of the performance of the Contract shall be waived under such policies. The Employer shall deliver to the Agency satisfactory evidence that the required insurances are in full force and effect. The policies shall provide that not less than twenty-one (21) days’ notice shall be given to the Agency by all insurers prior to any cancellation or material modification of the policies. If so requested by the Agency, the Employer shall provide copies of the policies taken out by the Employer under this GCC Sub-Clause 31.5. 31.6 If the Agency fails to take out and/or maintain in effect the insurances referred to in GCC Sub-Clause 31.1, the Employer may take out and maintain in effect any such insurances and may from time to time deduct from any amount due the Agency under the Contract any premium that the Employer shall have paid to the insurer, or may otherwise recover such amount as a debt due from the Agency. If the Employer fails to take out and/or maintain in effect the insurances referred to in GCC 31.5, the Agency may take out and maintain in effect any such insurances and may from time to time deduct from any amount due the Employer under the Contract any premium that the Agency shall have paid to the insurer, or may otherwise recover such amount as a debt due from the Employer. If the Agency fails to or is unable to take out and maintain in effect any such insurances, the Agency shall nevertheless have no liability or responsibility towards the Employer, and the Agency shall have full recourse against the Employer for any and all liabilities of the Employer herein. 31.7 Unless otherwise provided in the Contract, the Agency shall prepare and conduct all and any claims made under the policies affected by it pursuant to this GCC Clause 31, and all monies payable by any insurers shall be paid to the Agency. The Employer shall give to the Agency all such reasonable assistance as may be required by the Agency. With respect to insurance claims in which the Employer’s interest is involved, the Agency shall not give any release or make any compromise with the insurer without the prior written consent of the Employer. With respect to insurance claims in which the Agency’s interest is involved, the Employer shall not give any release or make any compromise with the insurer without the prior written consent of the Agency. |
| 32 | Unforeseen Conditions | 32.1 If, during the execution of the Contract, the Agency shall encounter on the Site any physical conditions other than climatic conditions, or artificial obstructions that could not have been reasonably foreseen prior to the date of the Contract Agreement by an experienced agency on the basis of reasonable examination of the data relating to the Works including any data as to boring tests, provided by the Employer, and on the basis of information that it could have been obtained from a visual inspection of the Site if access thereto was available, or other data readily available to it relating to the Works, and if the Agency determines that it will in consequence of such conditions or obstructions incur additional cost and expense or require additional time to perform its obligations under the Contract that would not have been required if such physical conditions or artificial obstructions had not been encountered, the Agency shall promptly, and before performing additional work or using additional Plant or Agency’s Equipment, notify the Project Manager in writing of (a) the physical conditions or artificial obstructions on the Site that could not have been reasonably foreseen; (b) the additional work and/or Plant and/or Agency’s Equipment required, including the steps which the Agency will or proposes to take to overcome such conditions or obstructions; (c) the extent of the anticipated delay; and (d) the additional cost and expense that the Agency is likely to incur. On receiving any notice from the Agency under this GCC Sub-Clause 32.1, the Project Manager shall promptly consult with the Employer and Agency and decide upon the actions to be taken to overcome the physical conditions or artificial obstructions encountered. Following such consultations, the Project Manager shall instruct the Agency, with a copy to the Employer, of the actions to be taken. 32.2 Any reasonable additional cost and expense incurred by the Agency in following the instructions from the Project Manager to overcome such physical conditions or artificial obstructions referred to in GCC Sub-Clause 32.1 shall be paid by the Employer to the Agency as an addition to the Contract Price. 32.3 If the Agency is delayed or impeded in the performance of the Contract because of any such physical conditions or artificial obstructions referred to in GCC Sub-Clause 32.1, the Time for Completion shall be extended in accordance with GCC Clause 36. |
| 33 | Change in Laws and Regulations | 33.1 If, after the date twenty-eight (28) days prior to the date of Bid submission, any law, regulation, ordinance, order or by-law having the force of law is enacted, promulgated, abrogated or changed which shall be deemed to include any change in interpretation or application by the competent authorities, that subsequently affects the costs and expenses of the Agency and/or the Time for Completion, the Contract Price shall be correspondingly increased or decreased, and/or the Time for Completion shall be reasonably adjusted to the extent that the Agency has thereby been affected in the performance of any of its obligations under the Contract. Notwithstanding the foregoing, such additional or reduced costs shall not be separately paid or credited if the same has already been accounted for in the price adjustment provisions where applicable, in accordance with the SCC, pursuant to GCC Sub-Clause 11.2. |
| 34 | Force Majeure | 34.1 “Force Majeure” shall mean any event beyond the reasonable control of the Employer or of the Agency, as the case may be, and which is unavoidable notwithstanding the reasonable care of the party affected, and shall include, without limitation, the following: (a) war, hostilities or warlike operations whether a state of war be declared or not, invasion, act of foreign enemy and civil war (b) rebellion, revolution, insurrection, mutiny, usurpation of civil or military government, conspiracy, riot, civil commotion and terrorist acts (c) confiscation, nationalization, mobilization, commandeering or requisition by or under the order of any government or de jure or de facto authority or ruler or any other act or failure to act of any local state or national government authority (d) strike, sabotage, lockout, embargo, import restriction, port congestion, lack of usual means of public transportation and communication, industrial dispute, shortage or restriction of power supply, epidemics, quarantine and plague (e) earthquake, landslide, volcanic activity, fire, flood or inundation, cyclone, storm, lightning, or other inclement weather condition, nuclear and pressure waves or other natural or physical disaster (f) shortage of labor, materials or utilities where caused by circumstances that are themselves Force Majeure. 34.2 If either party is prevented, hindered or delayed from or in performing any of its obligations under the Contract by an event of Force Majeure, then it shall notify the other in writing of the occurrence of such event and the circumstances thereof within fourteen (14) days after the occurrence of such event. 34.3 The party who has given such notice shall be excused from the performance or punctual performance of its obligations under the Contract for so long as the relevant event of Force Majeure continues and to the extent that such party’s performance is prevented, hindered or delayed. The Time for Completion shall be extended in accordance with GCC Clause 36. 34.4 The party or parties affected by the event of Force Majeure shall use reasonable efforts to mitigate the effect thereof upon its or their performance of the Contract and to fulfill its or their obligations under the Contract, but without prejudice to either party’s right to terminate the Contract under GCC Sub-Clause 38. 34.5 No delay or nonperformance by either party hereto caused by the occurrence of any event of Force Majeure shall (a) constitute a default or breach of the Contract, or (b) give rise to any claim for damages or additional cost or expense occasioned thereby, subject to GCC Sub-Clause 29.2. if and to the extent that such delay or nonperformance is caused by the occurrence of an event of Force Majeure. 34.6 If the performance of the Contract is substantially prevented, hindered or delayed for a single period of more than sixty (60) days or an aggregate period of more than one hundred and twenty (120) days on account of one or more events of Force Majeure during the currency of the Contract, the parties will attempt to develop a mutually satisfactory solution, failing which either party may terminate the Contract by giving a notice to the other, but without prejudice to either party’s right to terminate the Contract under GCC Clause 38. 34.7 In the event of termination pursuant to GCC Sub-Clause 34.6, the rights and obligations of the Employer and the Agency shall be as specified in GCC Sub-Clauses 38.1.2 and 38.1.3. 34.8 Notwithstanding GCC Sub-Clause 34.5, Force Majeure shall not apply to any obligation of the Employer to make payments to the Agency herein. |
| G | Change in Contract Elements |
| 35 | Change in the Works | 35.1 Introducing a Change 35.1.1 Subject to GCC Sub-Clauses 35.2.5 and 35.2.7, the Employer shall have the right to propose, and subsequently require, that the Project Manager order the Agency from time to time during the performance of the Contract to make any change, modification, addition or deletion to, in or from the Works hereinafter called “Change”, provided that such Change falls within the general scope of the Works and does not constitute unrelated work and that it is technically practicable, taking into account both the state of advancement of the Works and the technical compatibility of the Change envisaged with the nature of the Works as specified in the Contract. 35.1.2 The Agency may from time to time during its performance of the Contract propose to the Employer with a copy to the Project Manager, any Change that the Agency considers necessary or desirable to improve the quality, efficiency or safety of the Works. The Employer may at its discretion approve or reject any Change proposed by the Agency, provided that the Employer shall approve any Change proposed by the Agency to ensure the safety of the Works. 35.1.3 Notwithstanding GCC Sub-Clauses 35.1.1 and 35.1.2, no change made necessary because of any default of the Agency in the performance of its obligations under the Contract shall be deemed to be a Change, and such change shall not result in any adjustment of the Contract Price or the Time for Completion. 35.1.4 The procedure on how to proceed with and execute Changes is specified in GCC Sub-Clauses 35.2 and 35.3, and further details and forms are provided in the Employer’s Requirements (Forms and Procedures). 35.2 Changes Originating from Employer 35.2.1 If the Employer proposes a Change pursuant to GCC Sub-Clause 35.1.1, it shall send to the Agency a “Request for Change Proposal,” requiring the Agency to prepare and furnish to the Project Manager as soon as reasonably practicable a “Change Proposal,” which shall include the following: (a) brief description of the Change (b) effect on the Time for Completion (c) estimated cost of the Change (d) effect on Functional Guarantees (if any) (e) effect on the Works (f) effect on any other provisions of the Contract. 35.2.2 Prior to preparing and submitting the “Change Proposal,” the Agency shall submit to the Project Manager an “Estimate for Change Proposal,” which shall be an estimate of the cost of preparing and submitting the Change Proposal. Upon receipt of the Agency’s Estimate for Change Proposal, the Employer shall do one of the following: (a) accept the Agency’s estimate with instructions to the Agency to proceed with the preparation of the Change Proposal (b) advise the Agency of any part of its Estimate for Change Proposal that is unacceptable and request the Agency to review its estimate (c) advise the Agency that the Employer does not intend to proceed with the Change. 35.2.3 Upon receipt of the Employer’s instruction to proceed under GCC Sub-Clause 35.2.2 (a), the Agency shall, with proper expedition, proceed with the preparation of the Change Proposal, in accordance with GCC Sub-Clause 35.2.1. 35.2.4 The pricing of any Change shall, as far as practicable, be calculated in accordance with the rates and prices included in the Contract. If such rates and prices are inequitable, the parties thereto shall agree on specific rates for the valuation of the Change. 35.2.5 If before or during the preparation of the Change Proposal it becomes apparent that the aggregate effect of compliance therewith and with all other Change Orders that have already become binding upon the Agency under this GCC Clause 35 would be to increase or decrease the Contract Price as originally set forth in Article 2 (Contract Price) of the Contract Agreement by more than fifteen percent (15%), the Agency may give a written notice of objection thereto prior to furnishing the Change Proposal as aforesaid. If the Employer accepts the Agency’s objection, the Employer shall withdraw the proposed Change and shall notify the Agency in writing thereof. The Agency’s failure to so object shall neither affect its right to object to any subsequent requested Changes or Change Orders herein, nor affect its right to take into account, when making such subsequent objection, the percentage increase or decrease in the Contract Price that any Change not objected to by the Agency represents. 35.2.6 Upon receipt of the Change Proposal, the Employer and the Agency shall mutually agree upon all matters therein contained. Within seven (7) days after such agreement, the Employer shall, if it intends to proceed with the Change, issue the Agency with a Change Order. If the Employer is unable to reach a decision within seven (7) days, it shall notify the Agency with details of when the Agency can expect a decision. If the Employer decides not to proceed with the Change for whatever reason, it shall, within the said period of seven (7) days, notify the Agency accordingly. Under such circumstances, the Agency shall be entitled to reimbursement of all costs reasonably incurred by it in the preparation of the Change Proposal, provided that these do not exceed the amount given by the Agency in its Estimate for Change Proposal submitted in accordance with GCC Sub-Clause 35.2.2. 35.2.7 If the Employer and the Agency cannot reach agreement on the price for the Change, an equitable adjustment to the Time for Completion, or any other matters identified in the Change Proposal, the Employer may nevertheless instruct the Agency to proceed with the Change by issue of a “Pending Agreement Change Order.” Upon receipt of a Pending Agreement Change Order, the Agency shall immediately proceed with effecting the Changes covered by such Order. The parties shall thereafter attempt to reach agreement on the outstanding issues under the Change Proposal. If the parties cannot reach agreement within twenty (20) days from the date of issue of the Pending Agreement Change Order, then the matter may be referred under the Disputes and Arbitration Procedure in accordance with the provisions of GCC Sub-Clause 40. 35.3 Changes Originating from Agency 35.3.1 If the Agency proposes a Change pursuant to GCC Sub-Clause 35.1.2, the Agency shall submit to the Project Manager a written “Application for Change Proposal,” giving reasons for the proposed Change and including the information specified in GCC Sub-Clause 35.2.1. 35.4 Upon receipt of the Application for Change Proposal, the parties shall follow the procedures outlined in GCC Sub-Clauses 35.2.6 and 35.2.7. However, should the Employer choose not to proceed, the Agency shall not be entitled to recover the costs of preparing the Application for Change Proposal. |
| 36 | Extension of Time for Completion | 36.1 The Time(s) for Completion specified in the SCC shall be extended if the Agency is delayed or impeded in the performance of any of its obligations under the Contract by reason of any of the following: (a) any Change in the Works as provided in GCC Clause 35 (b) any occurrence of Force Majeure as provided in GCC Clause 34, unforeseen conditions as provided in GCC Clause 32, or other occurrence of any of the matters specified or referred to in paragraphs (a), (b) and (c) of GCC Sub-Clause 29.2 (c) any suspension order given by the Employer under GCC Clause 37 hereof or reduction in the rate of progress pursuant to GCC Sub-Clause 37.2 or (d) any changes in laws and regulations as provided in GCC Clause 33 or (e) any default or breach of the Contract by the Employer, or any activity, act or omission of the Employer, or the Project Manager, or any other agency employed by the Employer or (f) any other matter specifically mentioned in the Contract (g) any delay on the part of a sub-agency, provided such delay is due to a cause for which the Agency himself would have been entitled to an extension of time under this sub-clause by such period as shall be fair and reasonable in all the circumstances and as shall fairly reflect the delay or impediment sustained by the Agency. 36.2 Except where otherwise specifically provided in the Contract, the Agency shall submit to the Project Manager a notice of a claim for an extension of the Time for Completion, together with particulars of the event or circumstance justifying such extension as soon as reasonably practicable after the commencement of such event or circumstance. As soon as reasonably practicable after receipt of such notice and supporting particulars of the claim, the Employer and the Agency shall agree upon the period of such extension. In the event that the Agency does not accept the Employer’s estimate of a fair and reasonable time extension, the Agency shall be entitled to refer the matter to a Dispute Board, pursuant to GCC Sub-Clause 41. 36.3 The Agency shall at all times use its reasonable efforts to minimize any delay in the performance of its obligations under the Contract. In all cases where the Agency has given a notice of a claim for an extension of time under GCC 36.2, the Agency shall consult with the Project Manager in order to determine the steps (if any) which can be taken to overcome or minimize the actual or anticipated delay. The Agency shall thereafter comply with all reasonable instructions which the Project Manager shall give in order to minimize such delay. If compliance with such instructions shall cause the Agency to incur extra costs and the Agency is entitled to an extension of time under GCC 36.1, the amount of such extra costs shall be added to the Contract Price. |
| 37 | Suspension | 37.1 The Employer may request the Project Manager, by notice to the Agency, to order the Agency to suspend performance of any or all of its obligations under the Contract. Such notice shall specify the obligation of which performance is to be suspended, the effective date of the suspension and the reasons there for. The Agency shall thereupon suspend performance of such obligation, except those obligations necessary for the care or preservation of the Works, until ordered in writing to resume such performance by the Project Manager. If, by virtue of a suspension order given by the Project Manager, other than by reason of the Agency’s default or breach of the Contract, the Agency’s performance of any of its obligations is suspended for an aggregate period of more than thirty (30) days, then at any time thereafter and provided that at that time such performance is still suspended, the Agency may give a notice to the Project Manager requiring that the Employer shall, within fourteen (14) days of receipt of the notice, order the resumption of such performance or request and subsequently order a change in accordance with GCC Clause 35, excluding the performance of the suspended obligations from the Contract. If the Employer fails to do so within such period, the Agency may, by a further notice to the Project Manager, elect to treat the suspension, where it affects a part only of the Works, as a deletion of such part in accordance with GCC Clause 35 or, where it affects the whole of the Works, as termination of the Contract under GCC Sub-Clause 38.1. 37.2 If (a) the Employer has failed to pay the Agency any sum due under the Contract within the specified period, has failed to approve any invoice or supporting documents without just cause pursuant to the Appendix (Terms and Procedures of Payment) to the Contract Agreement, or commits a substantial breach of the Contract, the Agency may give a notice to the Employer that requires payment of such sum, with interest thereon as stipulated in GCC Sub-Clause 12.3, requires approval of such invoice or supporting documents, or specifies the breach and requires the Employer to remedy the same, as the case may be. If the Employer fails to pay such sum together with such interest, fails to approve such invoice or supporting documents or give its reasons for withholding such approval, or fails to remedy the breach or take steps to remedy the breach within seven (7) days after receipt of the Agency’s notice or (b) the Agency is unable to carry out any of its obligations under the Contract for any reason attributable to the Employer, including but not limited to the Employer’s failure to provide possession of or access to the Site or other areas in accordance with GCC Sub-Clause 10.2, or failure to obtain any governmental permit necessary for the execution and/or completion of the Works, then the Agency may by seven (7) days’ notice to the Employer suspend performance of all or any of its obligations under the Contract, or reduce the rate of progress. 37.3 If the Agency’s performance of its obligations is suspended or the rate of progress is reduced pursuant to this GCC Clause 37, then the Time for Completion shall be extended in accordance with GCC Sub-Clause 36.1, and any and all additional costs or expenses incurred by the Agency as a result of such suspension or reduction shall be paid by the Employer to the Agency in addition to the Contract Price, except in the case of suspension order or reduction in the rate of progress by reason of the Agency’s default or breach of the Contract. 41.4 During the period of suspension, the Agency shall not remove from the Site any Plant, any part of the Works or any Agency’s Equipment, without the prior written consent of the Employer. |
| 38 | Termination | 38.1 Termination for Employer’s Convenience 38.1.1 The Employer may at any time terminate the Contract for any reason by giving the Agency a notice of termination that refers to this GCC Sub-Clause 38.1. 38.1.2 Upon receipt of the notice of termination under GCC Sub-Clause 38.1.1, the Agency shall either immediately or upon the date specified in the notice of termination (a) cease all further work, except for such work as the Employer may specify in the notice of termination for the sole purpose of protecting that part of the Works already executed, or any work required to leave the Site in a clean and safe condition (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) (ii) below (c) remove all Agency’s Equipment from the Site, repatriate the Agency’s and its Sub-agency’ personnel from the Site, remove from the Site any wreckage, rubbish and debris of any kind, and leave the whole of the Site in a clean and safe condition, and (d) subject to the payment specified in GCC Sub-Clause 38.1.3, (i) deliver to the Employer the parts of the Works executed by the Agency up to the date of termination (ii) to the extent legally possible, assign to the Employer all right, title and benefit of the Agency to the Works and to the Plant as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Agency and its Sub-agency; and (iii) deliver to the Employer all non-proprietary drawings, specifications and other documents prepared by the Agency or its Sub-agency as at the date of termination in connection with the Works. 38.1.3 In the event of termination of the Contract under GCC Sub-Clause 38.1.1, the Employer shall pay to the Agency the following amounts: (a) the Contract Price, properly attributable to the parts of the Works executed by the Agency as of the date of termination (b) the costs reasonably incurred by the Agency in the removal of the Agency’s Equipment from the Site and in the repatriation of the Agency’s and its Sub-agency’ personnel (c) any amounts to be paid by the Agency to its Sub-agency in connection with the termination of any subcontracts, including any cancellation charges (d) costs incurred by the Agency in protecting the Works and leaving the Site in a clean and safe condition pursuant to paragraph (a) of GCC Sub-Clause 38.1.2 (e) the cost of satisfying all other obligations, commitments and claims that the Agency may in good faith have undertaken with third parties in connection with the Contract and that are not covered by paragraphs (a) through (d) above. 38.2 Termination for Agency’s Default 38.2.1 The Employer, without prejudice to any other rights or remedies it may possess, may terminate the Contract forthwith in the following circumstances by giving a notice of termination and its reasons there for to the Agency, referring to this GCC Sub-Clause 38.2: (a) if the Agency becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, or, if the Agency is a corporation, a resolution is passed or order is made for its winding up, other than a voluntary liquidation for the purposes of amalgamation or reconstruction, a receiver is appointed over any part of its undertaking or assets, or if the Agency takes or suffers any other analogous action in consequence of debt (b) if the Agency assigns or transfers the Contract or any right or interest therein in violation of the provision of GCC Clause 39. (c) if the Agency, in the judgment of the Employer has engaged in corrupt or fraudulent practices, as defined in GCC Clause 6, in competing for or in executing the Contract. 38.2.2 If the Agency (a) has abandoned or repudiated the Contract (b) has without valid reason failed to commence work on the Works promptly or has suspended, other than pursuant to GCC Sub-Clause 41.2, the progress of Contract performance for more than fourteen (14) days after receiving a written instruction from the Employer to proceed (c) persistently fails to execute the Contract in accordance with the Contract or persistently neglects to carry out its obligations under the Contract without just cause (d) refuses or is unable to provide sufficient materials, services or labor to execute and complete the Works in the manner specified in the program furnished under GCC Sub-Clause 18.2 at rates of progress that give reasonable assurance to the Employer that the Agency can attain Completion of the Works by the Time for Completion as extended, then the Employer may, without prejudice to any other rights it may possess under the Contract, give a notice to the Agency stating the nature of the default and requiring the Agency to remedy the same. If the Agency fails to remedy or to take steps to remedy the same within seven (7) days of its receipt of such notice, then the Employer may terminate the Contract forthwith by giving a notice of termination to the Agency that refers to this GCC Sub-Clause 38.2. 38.2.3 Upon receipt of the notice of termination under GCC Sub-Clauses 38.2.1 or 38.2.2, the Agency shall, either immediately or upon such date as is specified in the notice of termination, (a) cease all further work, except for such work as the Employer may specify in the notice of termination for the sole purpose of protecting that part of the Works already executed, or any work required to leave the Site in a clean and safe condition (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) below (c) deliver to the Employer the parts of the Works executed by the Agency up to the date of termination (d) to the extent legally possible, assign to the Employer all right, title and benefit of the Agency to the Works and to the Plant as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Agency and its Sub- agency (e) deliver to the Employer all drawings, specifications and other documents prepared by the Agency or its Sub-agency as of the date of termination in connection with the Works. 38.2.4 The Employer may enter upon the Site, expel the Agency, and complete the Works itself or by employing any third party. The Employer may, to the exclusion of any right of the Agency over the same, take over and use with the payment of a fair rental rate to the Agency, with all the maintenance costs to the account of the Employer and with an indemnification by the Employer for all liability including damage or injury to persons arising out of the Employer’s use of such equipment, any Agency’s Equipment owned by the Agency and on the Site in connection with the Works for such reasonable period as the Employer considers expedient for the construction of the Works. Upon completion of the Works or at such earlier date as the Employer thinks appropriate, the Employer shall give notice to the Agency that such Agency’s Equipment will be returned to the Agency at or near the Site and shall return such Agency’s Equipment to the Agency in accordance with such notice. The Agency shall thereafter without delay and at its cost remove or arrange removal of the same from the Site. 38.2.5 Subject to GCC Sub-Clause 38.2.6, the Agency shall be entitled to be paid the Contract Price attributable to the Works executed as of the date of termination, the value of any unused or partially used Plant on the Site, and the costs, if any, incurred in protecting the Works and in leaving the Site in a clean and safe condition pursuant to paragraph (a) of GCC Sub-Clause 38.2.3. Any sums due the Employer from the Agency accruing prior to the date of termination shall be deducted from the amount to be paid to the Agency under this Contract. 38.2.6 If the Employer completes the Works, the cost of completing the Works by the Employer shall be determined. If the sum that the Agency is entitled to be paid, pursuant to GCC Sub-Clause 38.2.5, plus the reasonable costs incurred by the Employer in completing the Works, exceeds the Contract Price, the Agency shall be liable for such excess. If such excess is greater than the sums due the Agency under GCC Sub-Clause 38.2.5, the Agency shall pay the balance to the Employer, and if such excess is less than the sums due the Agency under GCC Sub-Clause 38.2.5, the Employer shall pay the balance to the Agency. The Employer and the Agency shall agree, in writing, on the computation described above and the manner in which any sums shall be paid. 38.3 Termination by Agency 38.3.1 If (a) the Employer has failed to pay the Agency any sum due under the Contract within the specified period, has failed to approve any invoice or supporting documents without just cause pursuant to the Appendix (Terms and Procedures of Payment) to the Contract Agreement, or commits a substantial breach of the Contract, the Agency may give a notice to the Employer that requires payment of such sum, with interest thereon as stipulated in GCC Sub-Clause 12.3, requires approval of such invoice or supporting documents, or specifies the breach and requires the Employer to remedy the same, as the case may be. If the Employer fails to pay such sum , fails to approve such invoice or supporting documents or give its reasons for withholding such approval, fails to remedy the breach or take steps to remedy the breach within seven (7) days after receipt of the Agency’s notice, or (b) the Agency is unable to carry out any of its obligations under the Contract for any reason attributable to the Employer, including but not limited to the Employer’s failure to provide possession of or access to the Site or other areas or failure to obtain any governmental permit necessary for the execution and/or completion of the Works, then the Agency may give a notice to the Employer thereof, and if the Employer has failed to pay the outstanding sum, to approve the invoice or supporting documents, to give its reasons for withholding such approval, or to remedy the breach within fourteen (14) days of such notice, or if the Agency is still unable to carry out any of its obligations under the Contract for any reason attributable to the Employer within fourteen (14) days of the said notice, the Agency may by a further notice to the Employer referring to this GCC Sub-Clause 38.3.1, forthwith terminate the Contract. 38.3.2 The Agency may terminate the Contract forthwith by giving a notice to the Employer to that effect, referring to this GCC Sub-Clause 38.3.2, if the Employer becomes bankrupt or insolvent, has a receiving order issued against it, compounds with its creditors, if a receiver is appointed over any part of its undertaking or assets, or if the Employer takes or suffers any other analogous action in consequence of debt. 38.3.3 If the Contract is terminated under GCC Sub-Clauses 38.3.1 or 38.3.2, then the Agency shall immediately (a) cease all further work, except for such work as may be necessary for the purpose of protecting that part of the Works already executed, or any work required to leave the Site in a clean and safe condition (b) terminate all subcontracts, except those to be assigned to the Employer pursuant to paragraph (d) (ii) (c) remove all Agency’s Equipment from the Site and repatriate the Agency’s and its Sub-agency’ personnel from the Site, and (d) subject to the payment specified in GCC Sub-Clause 38.3.4, (i) deliver to the Employer the parts of the Works executed by the Agency up to the date of termination (ii) to the extent legally possible, assign to the Employer all right, title and benefit of the Agency to the Works and to the Plant as of the date of termination, and, as may be required by the Employer, in any subcontracts concluded between the Agency and its Sub-agency, and (iii) deliver to the Employer all drawings, specifications and other documents prepared by the Agency or its Sub-agency as of the date of termination in connection with the Works. 38.3.4 If the Contract is terminated under GCC Sub-Clauses 38.3.1 or 38.3.2, the Employer shall pay to the Agency all payments specified in GCC Sub-Clause 38.1.3, and reasonable compensation for all loss, except for loss of profit, or damage sustained by the Agency arising out of, in connection with or in consequence of such termination. 38.3.5 Termination by the Agency pursuant to this GCC Sub-Clause 38.3 is without prejudice to any other rights or remedies of the Agency that may be exercised in lieu of or in addition to rights conferred by GCC Sub-Clause 38.3. 38.4 In this GCC Clause 38, the expression “Works executed” shall include all work executed, Construction Services provided, and all equipment acquired, or subject to a legally binding obligation to purchase, by the Agency and used or intended to be used for the purpose of the Works, up to and including the date of termination. 38.5 In this GCC Clause 38, in calculating any monies due from the Employer to the Agency, account shall be taken of any sum previously paid by the Employer to the Agency under the Contract, including any advance payment paid pursuant to the Appendix (Terms and Procedures of Payment) to the Contract Agreement. |
| 39 | Assignment | 39.1 Neither the Employer nor the Agency shall, without the express prior written consent of the other party which consent shall not be unreasonably withheld, assign to any third party the Contract or any part thereof, or any right, benefit, obligation or interest therein or there under, except that the Agency shall be entitled to assign either absolutely or by way of charge any monies due and payable to it or that may become due and payable to it under the Contract. |
| H | Claims, Disputes and Arbitration |
| 40 | Agency’s Claims | 40.1 If the Agency considers himself to be entitled to any extension of the Time for Completion and/or any additional payment, under any Clause of these Conditions or otherwise in connection with the Contract, the Agency shall submit a notice to the Project Manager, describing the event or circumstance giving rise to the claim. The notice shall be given as soon as practicable, and not later than fourteen (14) days after the Agency became aware, or should have become aware, of the event or circumstance. If the Agency fails to give notice of a claim within such period of fourteen (14) days, the Time for Completion shall not be extended, the Agency shall not be entitled to additional payment, and the Employer shall be discharged from all liability in connection with the claim. The Agency shall keep such contemporary records as may be necessary to substantiate any claim, either on the Site or at another location acceptable to the Project Manager. Without admitting the Employer’s liability, the Project Manager may, after receiving any notice under this Sub-Clause, monitor the record-keeping and/or instruct the Agency to keep further contemporary records. The Agency shall permit the Project Manager to inspect all these records, and shall (if instructed) submit copies to the Project Manager. Within thirty (30) days after the Agency became aware (or should have become aware) of the event or circumstance giving rise to the claim, or within such other period as may be proposed by the Agency and approved by the Project Manager, the Agency shall send to the Project Manager a fully detailed claim which includes full supporting particulars of the basis of the claim and of the extension of time and/or additional payment claimed. If the event or circumstance giving rise to the claim has a continuing effect: this fully detailed claim shall be considered as interim; the Agency shall send further interim claims at monthly intervals, giving the accumulated delay and/or amount claimed, and such further particulars as the Project Manager may reasonably require; and the Agency shall send a final claim within twenty eight (28) days after the end of the effects resulting from the event or circumstance, or within such other period as may be proposed by the Agency and approved by the Project Manager. Within thirty (30) days after receiving a claim or any further particulars supporting a previous claim, or within such other period as may be proposed by the Project Manager and approved by the Agency, the Project Manager shall respond with approval, or with disapproval and detailed comments. He may also request any necessary further particulars, but shall nevertheless give his response on the principles of the claim within such time. Each Payment Certificate shall include such amounts for any claim as have been reasonably substantiated as due under the relevant provision of the Contract. Unless and until the particulars supplied are sufficient to substantiate the whole of the claim, the Agency shall only be entitled to payment for such part of the claim as he has been able to substantiate. The Project Manager shall agree with the Agency or estimate: (i) the extension (if any) of the Time for Completion (before or after its expiry) in accordance with GCC Clause 36, and/or (ii) the additional payment (if any) to which the Agency is entitled under the Contract. The requirements of this Sub-Clause are in addition to those of any other Sub-Clause which may apply to a claim. If the Agency fails to comply with this or another Sub-Clause in relation to any claim, any extension of time and/or additional payment shall take account of the extent (if any) to which the failure has prevented or prejudiced proper investigation of the claim, unless the claim is excluded under the second paragraph of this Sub-Clause. 40.2 In the event that the Agency and the Employer cannot agree on any matter relating to a claim, either party may refer the matter to the Disputes and Arbitration Procedure pursuant to GCC 41 hereof. |
| 41 | Disputes and Arbitration | 41.1 If a dispute (of any kind whatsoever) arises between the Parties in connection with the performance of the Contract, relating to the meaning of, or in any way whatsoever arising out of, the specifications, designs, drawings, estimates and instructions hereinbefore mentioned, or estimates concerning the works, or the execution or failure of the agency to execute the same, whether arising during the progress of the works or after the completion or abandonment thereof, including any dispute as to any certificate, determination, instruction, opinion or valuation of the Project Manager, either Party may refer the dispute in writing to the Superintending Engineer for decision, with copies to the other Party and the Project Manager. Such reference shall state that it is given under this Sub-Clause, and shall be made within a period of 14 days of such occurrence, except as otherwise provided for under this contract. Thereupon, the Superintending Engineer (SE) shall give his written instruction and/or decision within a period of 30 days of such request, which period can be extended by mutual consent of both parties. Upon receipt of written instructions or decisions of the SE by both parties, the parties shall promptly proceed without delay to comply with such instructions or decisions. If the Superintending Engineer fails to give his instructions or decision in writing within a period of 30 days or mutually agreed time, OR if after receipt of the of written instructions or decisions of the SE, either party is aggrieved against the decision of the SE, the party may within 14 days refer an appeal to the Chief Engineer who shall afford an opportunity to both parties to be heard and to offer evidence in support of or against the case. The Chief Engineer will give his decision within 30 days. If any party is not satisfied with the decision of the Chief Engineer, he can refer such dispute for arbitration by an Arbitration Board to be constituted by the State Government which shall consist of either one or three suitably qualified persons (“the members”), each of whom shall be fluent in the language for communication defined in the Contract and shall be a professional experienced in the type of activities involved in the performance of the Contract and with the interpretation of contractual documents. If the number is not so stated and the Parties do not agree otherwise, the Arbitration Board shall comprise three persons, one of whom shall serve as chairman. In such case each Party shall nominate one member for the approval of the other Party. The first two members shall recommend, and the Parties shall agree upon, the third member, who shall act as chairman. Both Parties shall promptly make available to the DB all such additional information, further access to the Site, and appropriate Works, as the DB may require for the purposes of making a decision on such dispute. The DB shall be deemed to be not acting as arbitrator(s). The arbitrator(s) shall have full power to open up, review and revise any certificate, determination, instruction, opinion or valuation of the Project Manager, and any decision relevant to the dispute. Nothing shall disqualify the Project Manager from being called as a witness and giving evidence before the arbitrator(s) on any matter whatsoever relevant to the dispute. Neither Party shall be limited in the proceedings before the arbitrator(s) to the evidence nor arguments previously put before the SE or CE to obtain their decision, or to the reasons for dissatisfaction given in its notice of dissatisfaction. Any decision of the SE or CE shall be admissible in evidence in the arbitration. Arbitration may be commenced prior to or after completion of the Works. The obligations of the Parties and the Project Manager shall not be altered by reason of any arbitration being conducted during the progress of the Works. |